## Gantt Chart
AI Tool Adoption Tracker - Microsoft Copilot Rollout
FinServ Corp (500 Employees) ¦ Prepared by: Kamala Simman Gopalakrishnan
WBS ID | Task / Work Package | Owner | Duration | Start Week | End Week | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
1.0 | PHASE 1 - ASSESSMENT AND PLANNING | PM | 2 weeks | 1 | 2 | █ | █
1.1 | Project Initiation | PM | 1 week | 1 | 1
1.1.1 | Draft and approve Project Charter | PM + COO | 1 week | 1 | 1
1.1.2 | Build Stakeholder Register | PM | 1 week | 1 | 1
1.1.3 | Define project scope and objectives | PM + COO | 1 week | 1 | 1
1.2 | Planning Documents | PM | 1 week | 2 | 2 | [16 empty] | LEGEND
1.2.1 | RACI Matrix | PM | 1 week | 2 | 2 | [17 empty] | Phase 1 - Assessment and Planning
1.2.2 | WBS and Gantt Chart | PM | 1 week | 2 | 2 | [17 empty] | Phase 2 - Pilot Program
1.2.3 | Risk Register (15 risks) | PM | 1 week | 2 | 2 | [17 empty] | Phase 3 - Full Rollout
1.2.4 | Communication Plan | PM | 1 week | 2 | 2 | [17 empty] | Phase 4 - Measurement and Closeout
1.2.5 | Training Plan (tiered) | PM + Trainer | 1 week | 2 | 2
1.3 | Readiness Assessment | PM + IT | 2 weeks | 1 | 2
1.3.1 | IT infrastructure compatibility check | IT Dir | 1 week | 1 | 1
1.3.2 | Change readiness survey (500 employees) | PM + HR | 1 week | 2 | 2
1.3.3 | Select pilot group (50 power users) | PM | 1 week | 2 | 2
2.0 | PHASE 2 - PILOT PROGRAM | PM | 4 weeks | 3 | 6 |  |  | █ | █ | █ | █
2.1 | Pilot Setup | PM + IT | 1 week | 3 | 3
2.1.1 | Activate 50 pilot licenses | IT + Vendor | 1 week | 3 | 3
2.1.2 | Configure Power BI pilot dashboard | PM | 1 week | 3 | 3
2.1.3 | Set up MS Forms pulse survey | PM + HR | 1 week | 3 | 3
2.2 | Pilot Training Delivery | Trainer | 2 weeks | 3 | 4
2.2.1 | Power user training sessions (8 hrs) | Trainer | 2 weeks | 3 | 4
2.2.2 | Distribute role specific use case guides | Trainer | 1 week | 4 | 4
2.3 | Pilot Monitoring and Feedback | PM | 3 weeks | 4 | 6
2.3.1 | Weekly adoption check ins | PM | 3 weeks | 4 | 6
2.3.2 | Monitor Power BI pilot metrics | PM | 3 weeks | 4 | 6
2.3.3 | Collect pilot pulse survey | PM + HR | 1 week | 5 | 5
2.4 | Pilot Closeout | PM + COO | 1 week | 6 | 6
2.4.1 | Conduct pilot retrospective | PM | 1 week | 6 | 6
2.4.2 | Go or No Go decision to COO | PM | 1 week | 6 | 6
2.4.3 | Integrate lessons into full rollout plan | PM | 1 week | 6 | 6
3.0 | PHASE 3 - FULL ROLLOUT | PM | 6 weeks | 7 | 12 | [6 empty] | █ | █ | █ | █ | █ | █
3.1 | Full Activation (450 users) | IT + Vendor | 1 week | 7 | 7
3.1.1 | Activate licenses for 450 remaining users | IT + Vendor | 1 week | 7 | 7
3.1.2 | Send rollout announcement to all staff | PM + COO | 1 week | 7 | 7
3.2 | Training Delivery - All Departments | Trainer | 4 weeks | 7 | 10
3.2.1 | Finance department training | Trainer | 2 weeks | 7 | 8
3.2.2 | HR department training | Trainer | 2 weeks | 8 | 9
3.2.3 | Operations department training | Trainer | 2 weeks | 9 | 10
3.2.4 | Department specific use case workshops | Trainer + PM | 4 weeks | 8 | 11
3.3 | Change Management and Adoption | PM + HR | 6 weeks | 7 | 12
3.3.1 | Weekly change champion circle meetings | PM + HR | 6 weeks | 7 | 12
3.3.2 | Monitor Change Resistance Heatmap | PM | 6 weeks | 7 | 12
3.3.3 | 1 on 1 coaching for Ops team leads | PM + Ops Mgr | 3 weeks | 8 | 10
3.4 | Power BI Dashboard - Live | PM | 6 weeks | 7 | 12
3.4.1 | Go live with Page 2 Productivity Impact | PM | 1 week | 7 | 7
3.4.2 | Go live with Page 3 ROI Dashboard | PM | 1 week | 8 | 8
3.4.3 | Weekly dashboard refresh and RAG reports | PM | 6 weeks | 7 | 12
3.5 | UAT and Hypercare Support | PM + IT | 4 weeks | 9 | 12
3.5.1 | User acceptance testing with dept leads | PM + IT | 3 weeks | 9 | 11
3.5.2 | Hypercare support desk (4 weeks) | IT Dir | 4 weeks | 9 | 12
3.5.3 | Collect Month 2 pulse survey | PM + HR | 1 week | 11 | 11
4.0 | PHASE 4 - MEASUREMENT AND CLOSEOUT | PM | 4 weeks | 13 | 16 | [12 empty] | █ | █ | █ | █
4.1 | Post Launch Measurement | PM | 2 weeks | 13 | 14
4.1.1 | Post launch productivity survey (500) | PM + HR | 1 week | 13 | 13
4.1.2 | Calculate final ROI vs $120K investment | PM | 1 week | 14 | 14
4.1.3 | Finalize Power BI with full project data | PM | 1 week | 14 | 14
4.2 | Executive Reporting | PM + COO | 1 week | 15 | 15
4.2.1 | Build ROI and Adoption Executive Report | PM | 1 week | 15 | 15
4.2.2 | Present results to C suite | PM + COO | 1 week | 15 | 15
4.3 | Project Closeout | PM | 1 week | 16 | 16
4.3.1 | Document Lessons Learned | PM | 1 week | 16 | 16
4.3.2 | Project closure and handoff to IT Ops | PM + IT | 1 week | 16 | 16
4.3.3 | Archive all project documents | PM | 1 week | 16 | 16